## Gantt
ExpenseMate – Project Gantt Chart
Software Construction & Development ¦ Team: Hamza Salahuddin (Member A), Rafay Ansari (Member B)
HOW TO USE: blue text on yellow = inputs (chart start date, task Start/End dates, Status). Days, phase rows and the bars are calculated automatically.
Chart start date: |  | 2026-09-23 | Final submission deadline: |  |  |  | 2026-09-27
Sep 2026
[8 empty] | Wed | Thu | Fri | Sat | Sun | Mon | Tue
Ph | ID | Task | Owner | Start | End | Days | Status | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-26 | 2026-09-27 | 2026-09-28 | 2026-09-29
1 | 1 | Phase 1 – Problem Definition & Requirements | Both | 2026-09-23 | 2026-09-23 | 1 | Done
1 | 1.1 | Write functional and non-functional requirements | Member A | 2026-09-23 | 2026-09-23 | 1 | Done
1 | 1.2 | Create use case diagram | Member B | 2026-09-23 | 2026-09-23 | 1 | Done
2 | 2 | Phase 2 – Architecture & Construction Planning | Both | 2026-09-24 | 2026-09-24 | 1 | In progress
2 | 2.1 | Choose architectural style (Client-Server, local) | Both | 2026-09-24 | 2026-09-24 | 1 | Done
2 | 2.2 | Draw Logical, Process, Physical, Deployment views | Member A | 2026-09-24 | 2026-09-24 | 1 | In progress
2 | 2.3 | Plan coding standards, tools and timeline | Member B | 2026-09-24 | 2026-09-24 | 1 | In progress
2 | 2.4 | Compile Architecture document + Gantt chart | Both | 2026-09-24 | 2026-09-24 | 1 | In progress
3 | 3 | Phase 3 – Coding & Unit Testing | Both | 2026-09-24 | 2026-09-25 | 2 | Not started
3 | 3.1 | Divide into modules; agree REST API contract | Both | 2026-09-24 | 2026-09-24 | 1 | Not started
3 | 3.2 | Backend: database, repositories, services, REST API | Member A | 2026-09-24 | 2026-09-25 | 2 | Not started
3 | 3.3 | Frontend: Tkinter screens, ApiClient, charts | Member B | 2026-09-24 | 2026-09-25 | 2 | Not started
3 | 3.4 | Write unit tests for own modules | Each member | 2026-09-25 | 2026-09-25 | 1 | Not started
4 | 4 | Phase 4 – Integration & System Testing | Both | 2026-09-25 | 2026-09-26 | 2 | Not started
4 | 4.1 | Integrate client and server modules | Both | 2026-09-25 | 2026-09-25 | 1 | Not started
4 | 4.2 | Perform integration testing | Member A | 2026-09-25 | 2026-09-26 | 2 | Not started
4 | 4.3 | Perform system testing | Member B | 2026-09-26 | 2026-09-26 | 1 | Not started
4 | 4.4 | Measure code complexity (cyclomatic) | Member A | 2026-09-26 | 2026-09-26 | 1 | Not started
4 | 4.5 | Track fault-find and fault-fix rates | Member B | 2026-09-25 | 2026-09-26 | 2 | Not started
5 | 5 | Phase 5 – Maintenance & Evolution | Both | 2026-09-26 | 2026-09-26 | 1 | Not started
5 | 5.1 | Add one new feature (adaptive maintenance) | Both | 2026-09-26 | 2026-09-26 | 1 | Not started
5 | 5.2 | Fix 2 bugs (corrective maintenance) | Member A | 2026-09-26 | 2026-09-26 | 1 | Not started
5 | 5.3 | Improve code quality (perfective maintenance) | Member B | 2026-09-26 | 2026-09-26 | 1 | Not started
5 | 5.4 | Apply Lehman's Laws analysis | Both | 2026-09-26 | 2026-09-26 | 1 | Not started
6 | 6 | Phase 6 – Final Report & Presentation | Both | 2026-09-25 | 2026-09-27 | 3 | Not started
6 | 6.1 | Write final report (3 pages) | Member B | 2026-09-25 | 2026-09-26 | 2 | Not started
6 | 6.2 | Prepare and rehearse system demo | Both | 2026-09-26 | 2026-09-26 | 1 | Not started
6 | 6.3 | Assemble final submission bundle | Both | 2026-09-26 | 2026-09-26 | 1 | Not started
6 | 6.4 | Submit final bundle (Team Lead) | Team Lead | 2026-09-27 | 2026-09-27 | 1 | Not started
Notes
• Instructor's deadline: Sunday 27 Sep 2026 (cell H4). The whole project (Phases 1-6) is planned for 23-26 Sep; 27 Sep is submission day.
• Phase 1 (SRS + Use Case Diagram) was done on 23 Sep. Phase 2 (architecture) is today, 24 Sep.
• Red-tinted column = deadline day; light-yellow column = today; grey columns = weekends. Change H4 and the task dates if the deadline moves.
• Owners follow the assignment: Member A = Hamza Salahuddin (backend), Member B = Rafay Ansari (frontend). 'Both' = whole team.
• Status drop-down: Not started / In progress / Done. Phase rows summarise their tasks automatically.